|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No.**Accelerating Nutrition Results in Nigeria (ANRiN) 2019 – 2020 Multisectoral Performance Table: Targets and Achievements (Sectoral Intervention in Gombe State** | Indicator | Baseline | 2019 target | Achieved | MOV Provided (Y/N) |
| Ministry of Finance, Budget and National Planning |  |
| 1.1 | Number of sectors implementing multi-sectoral plan  | 0 | 6 | 5 | YES (5 sectors implementing multi sectoral plan)  |
| 1.2 | Percentage of staff on ANRiN project in MBNP and five sectors trained on basic program management and computer application (MS Word, Excel and PowerPoint) | 0 | 80% | 91% | YES( Training reports and attendance of the participants |
| 1.3 | Updated data on results dashboard available from five sectors by November 31, 2019 | No | Yes | Yes | YES (Availability of data on results dashboard from five sectors)  |
|  | **Overall % achieved** |  **95%** |
| Federal Ministry of Health - Nutrition Division |  |
| 2.1 | Report of review of National Strategic Plan of Action for Nutrition (NSPAN) 2014-19 available | No | Yes |  | YES( Evaluation Report on NSPAN 2014-2019) |
| 2.2 | National Strategic Plan of Action for Nutrition (NSPAN) 2021 - 2025 | No | Yes |  | Ready for Printing and dissemination |
| 2.3 | Revised National Policy on Maternal, Infant and Young Child Nutrition (MIYCN) | No | Yes |  | Ready for Printing and dissemination |
| 2.4 | National Strategy on Maternal, Infant and Young Child Nutrition (MIYCN) | No | Yes |  | Ready for Printing and dissemination |
|  | **Overall % achieved**  |  **100%** |
| Federal Ministry of Woman Affairs and Social Development |  |
| 3.1 | Number of vulnerable women, adolescent girls and OVC trained on IGA | 0 | 300 | 600 | YES ( Attendance of the participants) |
| 3.2 | Number of women and adolescent self-help groups provided with nutrition-sensitive IGA equipment trained | 0 | 60 | 60 | YES(Attendance of the participants) |
| 3.3 | Percentage of vulnerable women and adolescent girls from NASSCO database in 3 intervention LGAs reached with nutrition messages | 0 | 300  | 1200  | YES ( The name and details of vulnerable and adolescent girls reached with nutrition messages) |
|  | **Overall % achieved** |  **100%** |
| NASSP |  |
| 4.1 | Rapid assessment report produced | No | Yes |  | YES ( Rapid Assessment report) |
| 4.2 | Directory of social sector programs, and nutrition services and institutions created | No | Yes |  | YES (Directory of social sector programs, and nutrition services and institutions) |
| 4.3 | Percentage of approved training completed | 0 | 60% | 100% | YES (Training Plan and reports) |
| 4.4 | Percentage/Number of PVHHs participated in food demonstration sessions | 0 | 60%(3500) | 100%(3507) | YES(Attendance of the participants) |
|  | **Overall % achieved** |  **100%** |
| Federal Ministry of Agriculture and Rural Development |  |
| 5.1 | Number of households in 3 intervention LGAs with established mixed backyard gardens for plants and small ruminants and poultry for animal protein  | 0 | 600 | 990 | YES (Names and details of the households with established mixed backyard gardens) |
| 5.2 | Number of households producing biofortified crops in 3 intervention LGAs | 0 | 600 | 990 | YES( Names and list of households producing biofortified crops in the 3 intervention LGA) |
| 5.3 | Training manual on the establishment of mixed home garden developed | No | Yes | Yes | YES (Training manual) |
| 5.4 | Number of trainers (including agriculture extension agents) trained on mixed home gardens in 3 intervention LGAs | 0 | 90 | 90 | YES (Attendance of the participants) |
|  | **Overall % achieved** |  **100%** |