|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No.**Accelerating Nutrition Results in Nigeria (ANRiN) 2021 – 2022 Multisectoral Performance Table: Targets and Achievements (Sectoral Intervention in Gombe State** | Indicator | Baseline | 2021 target | Achieved | MOV Provided (Y/N) |
| Ministry of Finance, Budget and National Planning |  |
| 1.1 | Number of sectors implementing multi-sectoral plan | 5 | 6 | 6 | 6 sectors implementing multi sectoral plan  |
| 1.2 | Percentage of staff on ANRiN project in MBNP and five sectors trained onresult-based monitoring and evaluation (RBM&E) of development projects  | 80% | 80% | 91% | Training reports and attendance of the participants |
| 1.3 | Percentage of staff on ANRiN project in MBNP and Five sectors and 2 officials from Gombe State trained on Programme Management(Intermediate). | 80% | 80% | 100% | Training reports and attendance of the participants |
| 1.4 | Updated data on results dashboard available from Six sectors by December 31, 2021 | No | Updated data on results dashboard available from Six sectors | Yes | Availability of data on results dashboard from six sectors  |
|  | **Overall % achieved** |  **99%** |
| Federal Ministry of Health - Nutrition Division |  |
| 2.1 | Report of review of National Strategic Plan of Action for Nutrition (NSPAN) 2014-19 available | No | Availability of report of the reviewed National Strategic Plan of Action for Nutrition (NSPAN) 2014-19 | Achieved |  Evaluation Report on NSPAN 2014-2019 |
| 2.2 | National Strategic Plan of Action for Nutrition (NSPAN) 2021 – 2025 | No | Availability of costed NSPAN 2(2019-2024) | Achieved | Printed copy of NSPAN (2019-2024) Available  |
| 2.3 | Revised National Policy on Maternal, Infant and Young Child Nutrition (MIYCN) | No | Availability of revised National MIYCN Policy | Achieved | Availability of validated copy |
| 2.4 | National Strategy on Maternal, Infant and Young Child Nutrition (MIYCN) | No | Availability of Validated MIYCN Strategy Document  | Achieved | Availability of validated copy |
|  | **Overall % achieved**  |  **80%** |
| Federal Ministry of Woman Affairs and Social Development |  |
| 3.1 | Number of vulnerable women, adolescent girls and OVC trained on IGA | 600 | 600 | 0 | NA |
| 3.2 | Number of women and adolescent self-help groups provided with nutrition-sensitive IGA equipment and training | 600 | 60 | 0 | NA |
| 3.3 | Percentage of vulnerable women and adolescent girls from NASSCO database in 3 intervention LGAs reached with nutrition messages | 3000 | 3000 | 900  | Report and attendance register |
|  | **Overall % achieved** |  **40%** |
| NASSP |  |
| 4.1 | Number of persons disaggregated by sectors, engaged to facilitate linkages of beneficiaries to available nutrition services in the 3 LGAs | No | 150 | Achieved | Engagement and sensitization report |
| 4.2 | Availability of the updated Directory of Social Sector Programmes; Nutrition services and institutions. | No | Yes | Achieved | Updated Directory of services produced |
| 4.3 | Number of CTFs/DOs that attended the food demonstration training | 0 | 63 | 100% Achieved |  Food demonstration training report and Attendance |
| 4.4 | Percentage/Number of PVHHs participated in food demonstration sessions | 3500 | 60% of 4000 (2400) | 100% achieved (3800) | Food demonstration sessions attendance registered in the MIS server |
|  | **Overall % achieved** |  **90%** |
| Federal Ministry of Agriculture and Rural Development |  |
| 5.1 | Number of households in 3 intervention LGAs with established mixed backyard gardens for plants and small ruminants and poultry for animal protein  | 600 | 400 | 615 | Reports, photographs, assessment reports |
| 5.2 | Number of households producing biofortified crops in 3 intervention LGAs | 990 |  400 | 615 | Reports, photographs, assessment reports |
| 5.3 | Training manual on the establishment of mixed home garden developed | No | Availability of training manual on the establishment of mixed home garden  | Developed and awaiting printing | Photographs of the workshop for the development of the manual, attendance register and draft training manual. |
| 5.4 | Number of trainers (including agriculture extension agents) trained on mixed home gardens in 3 intervention LGAs | 90 | 75 | 120 | Attendance sheet and training reports |
|  | **Overall % achieved 95%** |
|  | **Federal Ministry of Education** |
| 6.1 | Percentage of enrolled primary school children administered 2 doses of deworming tablets during the year disagregated by sex | 0 | 60%(26,485)) | 50% (22,046) | Education Secretaries Reports and documents |
| 6.2 | Percentage of primary school children administered weekly Iron Folate for 26 weeks during the year disaggregated by sex | 0 | 0% | 0% | NA- |
| 6.3 | Percentage of adolescent girls in secondary schools administered weekly Iron Folate for 26 weeks during the year disaggregated by sex | 0 | 60%(4,736) | 100%(7863) | Education Secretaries Reports and documents |
| 6.4 | Percentage of schools with nutrition clubs that hold atleast 2 WASH education sessions during the year disagregated by type of school (primary or secondary) | 0 | 60%(80 Schools) | 100%(142 Schools) | M&E Reports from Schools |
| Overall % achieved 70%   |