|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No.  **Accelerating Nutrition Results in Nigeria (ANRiN) 2021 – 2022 Multisectoral Performance Table: Targets and Achievements (Sectoral Intervention in Gombe State** | Indicator | Baseline | 2022 target | Achieved | MOV Provided (Y/N) |
| Ministry of Finance, Budget and National Planning | | | | |  |
| 1.1 | Number of sectors implementing multi-sectoral plan | 5 | 6 | 6 | 6 sectors implementing multi sectoral plan |
| 1.2 | Percentage of staff on ANRiN project in MBNP and five sectors trained onresult-based monitoring and evaluation (RBM&E) of development projects | 80% | 80% | 0 | 0 |
| 1.3 | Percentage of staff on ANRiN project in MBNP and Five sectors and 2 officials from Gombe State trained on Programme Management (Advance). | 80% | 80% | 90% | Training reports and attendance of the participants |
| 1.4 | Updated data on results dashboard available from Six sectors by December 31, 2021 | No | Updated data on results dashboard available from Six sectors | Yes | Availability of data on results dashboard from six sectors |
| 1.5 | National Nutrition Data and Result Conference | NO | Conduct of National Nutrition and Result Conference | YES (Conducted) | Report of NNDRC |
|  | **Overall % achieved** | **90%** | | | |
| Federal Ministry of Health - Nutrition Division | | | | |  |
| 2.1 | Report of review of National Strategic Plan of Action for Nutrition (NSPAN) 2014-19 available | No | Availability of report of the reviewed National Strategic Plan of Action for Nutrition (NSPAN) 2014-19 | Achieved | Evaluation Report on NSPAN 2014-2019 |
| 2.2 | National Strategic Plan of Action for Nutrition (NSPAN) 2021 – 2025 | No | Availability of costed NSPAN 2(2019-2024) | Achieved | Printed copy of NSPAN (2019-2024) Available |
| 2.3 | Revised National Policy on Maternal, Infant and Young Child Nutrition (MIYCN) | No | Availability of revised National MIYCN Policy | Achieved | Availability of validated copy |
| 2.4 | National Strategy on Maternal, Infant and Young Child Nutrition (MIYCN) | No | Availability of Validated MIYCN Strategy Document | Achieved | Availability of validated copy |
|  | **Overall % achieved** | **80%** | | | |
| Federal Ministry of Woman Affairs and Social Development | | | | |  |
| 3.1 | Number of vulnerable women, adolescent girls and OVC trained on IGA | 600 | 600 | 600 | Training reports and attendance of participants |
| 3.2 | Number of women and adolescent self-help groups provided with nutrition-sensitive IGA equipment and training | 600 | 60 | 60 | Training reports and attendance of participants |
| 3.3 | Percentage of vulnerable women and adolescent girls from NASSCO database in 3 intervention LGAs reached with nutrition messages | 3000 | 3000 | 900 | Reports and attendance register |
|  | **Overall % achieved** | **77%** | | | |
| NASSP | | | | |  |
| 4.1 | Number of persons disaggregated by sectors, engaged to facilitate linkages of beneficiaries to available nutrition services in the 3 LGAs | No | 150 | Achieved | Engagement and sensitization report |
| 4.2 | Availability of the updated Directory of Social Sector Programmes; Nutrition services and institutions. | No | Yes | Achieved | Updated Directory of services produced |
| 4.3 | Number of CTFs/DOs that attended the food demonstration training | 0 | 63 | 100% Achieved | Food demonstration training reports and attendance |
| 4.4 | Percentage/Number of PVHHs participated in food demonstration sessions | 3500 | 60% of 4000 (2400) | 100% achieved (3800) | Food demonstration sessions attendance registered in the MIS server |
|  | **Overall % achieved** | **90%** | | | |
| Federal Ministry of Agriculture and Rural Development | | | | |  |
| 5.1 | Number of households in 3 intervention LGAs with established mixed backyard gardens for plants and small ruminants and poultry for animal protein | 600 | 400 | 615 | Reports, photographs, assessment reports |
| 5.2 | Number of households producing biofortified crops in 3 intervention LGAs | 990 | 400 | 615 | Reports, photographs, assessment reports |
| 5.3 | Training manual on the establishment of mixed home garden developed | No | Availability of training manual on the establishment of mixed home garden | Developed and awaiting printing | Photographs of the workshop for the development of the manual, attendance register and draft training manual. |
| 5.4 | Number of trainers (including agriculture extension agents) trained on mixed home gardens in 3 intervention LGAs | 90 | 75 | 120 | Attendance sheet and training reports |
|  | **Overall % achieved 95%** | | | | |
|  | **Federal Ministry of Education** | | | | |
| 6.1 | Number of enrolled primary school children administered 2 doses of deworming tablet during the year disaggregated by sex | 0 | 60%  (26,485)) | 50%  (22,046) | Registered of children administered deworming tablets and reports of deworming exercise |
| 6.2 | Number of primary school children adminstered weekly Iron Foliate for 25 weeks during the year. | 0 | 0% | 0% | Registered of children administered Iron foliate and reports of distribution exercise |
| 6.3 | Number of menstruating adolescent girl in secondary schools administered weekly Iron foliate for 26 weeks during the year. | 0 | 60%  (4,736) | 100%  (7863) | Register of menstruating adolescent girls administered weekly Iron foliate and reports of distribution exercise |
| 6.4 | Number of WASH Education session conducted during the year disaggregated by type of school (primary or secondary) | 0 | 60%  (80 Schools) | 100%  (142 Schools) | Reports of WASH education sessions conducted |
| 6.5 | Number of teachers trained on nutrition education at least twice during the year disaggregated by type of school (primary or secondary) | 0 | 60% | 100% | Reports of nutrition education conducted |
| Overall % achieved 70% | | | | | |